## 1. README
KNNO Coffee — Phase Financials & Risk Workbook
v2 · 2026-05-11 · Phase 1 prep list aligned with user-supplied equipment + certs requirements
How to use this workbook
Color convention | BLUE = inputs you change · BLACK = formulas · GREEN = cross-sheet references · YELLOW background = key assumptions to revisit
Update sequence | 1. Review Phase 1 Budget (line items now mirror your prep list). 2. Update Phase 1 Revenue assumptions. 3. After carboot pop-ups, enter Decision Gate actuals. 4. Read decision flag.
Currency | All figures in RM (Malaysian Ringgit) unless stated.
What changed in v2 | Sub-phase 1B rewritten to match your actual prep list (proper coffee cart with water pump+sink, 4 drippers, brand banner, etc.). New Sub-phase 1D for certs (typhoid jab, food handling permit, car boot permit). Phase 2 capex reduced where Phase 1 already covers (cart, brand identity).
Sheet | Purpose
1. README | This sheet
2. P1 Budget | Indonesia R&D + Carboot prep (your prep list) + Carboot ops + Certs. Min/Base/Max ranges.
3. P1 Revenue | Carboot pop-up revenue model. 3 scenarios (Bear/Base/Bull). 4 pop-ups.
4. P1 Net Cash | Net cash after Phase 1 = revenue − cost. Reusable equipment carry-over.
5. P2 Capex | Build phase capex (reduced — cart and brand identity already in Phase 1).
6. Combined Capex | Master view: P1 + P2 vs RM 15K budget. Trim options.
7. Decision Gate | P1→P2 weighted scoring. 10 criteria. Auto-classifies GO / HOLD / NO-GO.
8. P1 Risks | Phase 1 risk register. L×I = score. Auto-coloured.
9. P1 Sensitivity | Cups × ticket revenue matrix vs Phase 1 cost.
10. Cash Tracker | Week -8 → +12 running cash position.
Decision rules | Sheet 7 thresholds: ≥85% = GO. 70–85% = GO with cautions. 55–70% = HOLD. <55% = NO-GO.
Linked vault docs | 08-Action Plan & Timeline.md · 09-Financial Projections (Conservative).md · 07-Risks & Failure Modes.md · 02-Market Analysis & Validation.md · 06-Suppliers & Co-Roasting.md

## 2. P1 Budget
PHASE 1 BUDGET — Indonesia R&D + Carboot Validation (v2 — your prep list)
All RM. Min/Base/Max are honest range estimates. "Reusable" = carries into Phase 2 (reduces P2 capex).
Sub-phase 1A — F1 to Indonesia (~10–14 days)
# | Line item | Min | Base | Max | Reusable? | Notes
1A.1 | Flight to Bandung (return, AirAsia/MAS economy) | 800 | 1000 | 1200 | No | Book 4+ weeks ahead
1A.2 | Accommodation 7–10 nights | 700 | 950 | 1200 | No | Guesthouse / mid Airbnb
1A.3 | Roastery rental fees (sample roaster) | 200 | 350 | 500 | No | Producer site = often free
1A.4 | Green coffee bought in Indonesia (8–12 kg) | 800 | 1150 | 1500 | Partial | 5–8 kg flows to Phase 2 production
1A.5 | Local transport (Grab, Gojek, intercity) | 200 | 300 | 450 | No | 10–14 days of movement
1A.6 | Food & per diem (~RM 60–80/day × 10 days) | 400 | 600 | 800 | No | Local meals
1A.7 | Vacuum bags + import declaration prep | 50 | 100 | 150 | No | Packaging for transit
1A.8 | Contingency (10% of itemised) | 315 | 445 | 580 | No | Standard 10% buffer
| Sub-phase 1A subtotal | 3465 | 4895 | 6380
Sub-phase 1B — Coffee Cart + Equipment Prep (your prep list)
# | Line item | Min | Base | Max | Reusable? | Notes
1B.1 | Coffee cart with water pump + sink (mobile, manual-brew config) | 1500 | 2200 | 3000 | Yes | Carries into Phase 2; may need finish/upgrade in P2
1B.2 | Glassware (cupping/serving glasses, demitasses, tasters) | 150 | 220 | 300 | Yes | For carboot cupping moments + flight serves
1B.3 | Paper / plastic cups + lids (initial 250 units) | 80 | 120 | 180 | Partial | Generic at first; branded sleeves over the top
1B.4 | Hand grinder (Comandante or equivalent) | 700 | 800 | 950 | Yes | Reusable as filter/backup grinder in Phase 2
1B.5 | V60 drippers ×3 — Hario Switch where possible | 450 | 520 | 600 | Yes | Switches enable hybrid immersion-percolation; speeds parallel service
1B.6 | Origami dripper ×1 (4th total dripper) | 200 | 250 | 320 | Yes | Different geometry/profile vs V60s
1B.7 | V60 + Origami servers/jugs (×4) | 120 | 180 | 260 | Yes | Hario range server or equivalent
1B.8 | Brewista kettle (electric gooseneck) | 380 | 480 | 600 | Yes | Variable-temp model preferred
1B.9 | Paper filters (V60 02 + Origami, initial stock) | 80 | 120 | 180 | No | Replenished per pop-up
1B.10 | Brewing scales ×2 (Acaia / Hario) | 280 | 400 | 700 | Yes | Two scales for parallel brewing
1B.11 | Brand identity full delivery (logo + ID system v1, full not deposit) | 1000 | 1500 | 2200 | Yes | Required so banner + lot cards carry KNNO design
1B.12 | Branded banner (vinyl, with brandkit + design) | 250 | 380 | 550 | Yes | Vinyl banner ~2m×1m, retractable stand if possible
1B.13 | Lot story cards (60 prints, on-brand) | 60 | 100 | 150 | No | Print-on-demand once brand v1 delivered
1B.14 | Foldable seats ×4 (small bistro stools) | 200 | 320 | 480 | Yes | Customer dwell + brand dwell time
1B.15 | Foldable small tables ×2 | 200 | 320 | 480 | Yes | For seated customers + display
1B.16 | IG poll/V2 + V5 small ad amplification | 0 | 50 | 150 | No | Optional small boost
1B.17 | Contingency (10% of itemised) | 565 | 796 | 1110 | No | Standard 10% buffer
| Sub-phase 1B subtotal | 6215 | 8756 | 12210
Sub-phase 1C — Carboot Validation Pop-Ups (4 events, ops-only)
# | Line item | Min | Base | Max | Reusable? | Notes
1C.1 | Venue fees (4 events; mostly free, 1–2 paid) | 0 | 200 | 400 | No | Friend cafes free; small market sublet RM 100–200
1C.2 | Per-event consumables: extra cups, lids, sleeves (4 events) | 240 | 320 | 400 | No | Beyond initial stock in 1B.3
1C.3 | Milk + oat milk (4 events) | 80 | 120 | 180 | No | ~1L per event, whole + oat
1C.4 | Transport / Grab / fuel (4 events) | 120 | 200 | 320 | No | Cart kit transport
1C.5 | Sundries (napkins, sanitiser, bin liners, water cups) | 100 | 160 | 240 | No | Bulk-buy once
1C.6 | Validation V1 reward (30 friends taste test) | 0 | 80 | 150 | No | Optional thank-you
| Sub-phase 1C subtotal | 540 | 1080 | 1690
Sub-phase 1D — Certs & Permits (your prep list)
# | Line item | Min | Base | Max | Reusable? | Notes
1D.1 | Typhoid vaccination + cert (×2 founders) | 160 | 220 | 300 | No | KKM food handler health screening; ~RM 80–150 per person
1D.2 | Food handling permit + course (×2 founders) | 60 | 110 | 160 | No | KKM food handler course + permit; ~RM 30–80 per person
1D.3 | Car Boot / Roving Hawker permit (DBKL or local council) | 100 | 200 | 300 | No | Validity period varies; renew annually
1D.4 | Public liability insurance (1st year) | 600 | 800 | 1200 | No | Covers carboot + Phase 2 cart events
1D.5 | SSM business registration (Sole Prop or Sdn Bhd) | 60 | 1000 | 1500 | No | Sole Prop = RM 60/yr; Sdn Bhd = RM 1K+ setup
| Sub-phase 1D subtotal | 980 | 2330 | 3460
| PHASE 1 TOTAL OUT-OF-POCKET | 11200 | 17061 | 23740
| of which: Reusable equipment (carries to Phase 2) | 5430 | 7570 | 10440
| Phase 1 NET burn (out-of-pocket less reusable equipment) | 5770 | 9491 | 13300
Tip: change BLUE inputs above (Min/Base/Max). Subtotals + totals recalculate automatically.

## 3. P1 Revenue
PHASE 1 REVENUE — Carboot Pop-Ups (4 events)
Per-event scenarios. BLUE = inputs.
Per-Pop-Up Assumptions
# | Variable | Bear | Base | Bull | Notes
R.1 | Cups served per pop-up | 25 | 40 | 65 | Bear=friends only · Base=walk-up converts · Bull=well-attended venue
R.2 | Avg ticket price (RM/cup) | 12 | 13 | 14 | Carboot pricing — slightly under Phase 4 menu
R.3 | Bag sales per pop-up (units) | 0 | 1 | 3 | Pre-bagged 100g samplers
R.4 | Avg bag price (RM) | 30 | 35 | 40 | Lo-fi 100g sampler
R.5 | Tip / extra contribution (avg RM/cup) | 0 | 0.5 | 1.5 | Optional tip jar
| Per pop-up revenue | 300 | 575 | 1127.5
R.6 | Number of pop-ups in Phase 1 | 4 | 4 | 4 | Per action plan §4 sub-phase 1C
| PHASE 1 TOTAL REVENUE (all 4 pop-ups) | 1200 | 2300 | 4510
Per-Pop-Up Detail (4 events)
Event | Venue type | Bear | Base | Bull | Notes
Pop-up #1 | Friend office tower lobby (Wed) | 300 | 575 | 1127.5 | Lower foot traffic; office crowd
Pop-up #2 | Friend cafe carpark/patio (Sat) | 300 | 575 | 1127.5 | Weekend; established cafe traffic
Pop-up #3 | Creative space courtyard (Sun) | 300 | 575 | 1127.5 | Tests new audience
Pop-up #4 | Strongest venue repeat OR new format | 300 | 575 | 1127.5 | Repeat builds repeat-rate signal
| Sum check | 1200 | 2300 | 4510
Note: each pop-up modelled at average per-event revenue. Real variance high — Pop-up #1 likely under, #2/#4 likely over.

## 4. P1 Net Cash
PHASE 1 NET CASH POSITION — Combined view
Pulls from sheets 2 (Budget) and 3 (Revenue). Shows net burn after carboot revenue.
Component | Bear | Base | Bull | Notes
Phase 1 Cost (Total out-of-pocket) | 11200 | 17061 | 23740 | Min=Bear, Max=Bull
Less: Reusable equipment (carries to Phase 2) | 5430 | 7570 | 10440 | Investment, not lost spend
Phase 1 NET equipment burn | 5770 | 9491 | 13300 | True cost lost in Phase 1
Phase 1 Revenue (4 carboot pop-ups) | 1200 | 2300 | 4510 | From P1 Revenue sheet
NET CASH POSITION after Phase 1 (revenue − net burn) | -4570 | -7191 | -8790 | Negative = expected for validation phase
Phase 1 Cash Recovery Rate (Revenue / Net Burn) | 20.8% | 24.23% | 33.91% | >50% = strong validation pricing power
Reading the result
• Negative net cash after Phase 1 is EXPECTED. Phase 1 is validation, not revenue.
• Net burn in v2 is HIGHER than v1 — your prep list (proper cart, branded banner, 4 drippers, certs) is ~RM 4–5K more than the lo-fi v1 estimate. Reusable equipment offsets most of this in Phase 2.
• Cash Recovery Rate >50% = strong pricing power signal. <30% = revisit Phase 4 pricing.
• The NET equipment burn (truly "lost") is much smaller than the out-of-pocket cost, because most equipment carries to Phase 2.

## 5. P2 Capex
PHASE 2 BUILD CAPEX — Reduced (cart and brand identity carry from Phase 1)
Phase 2 launches once Phase 1 Decision Gate clears. Items already covered in Phase 1 are reduced or removed.
# | Line item | Min | Base | Max | Carry from P1? | Notes
2.01 | Cart upgrade/finish (cart base from Phase 1, finish + signage) | 400 | 800 | 1500 | Yes (base) | Phase 1 cart upgraded for full menu; not full new cart
2.02 | Espresso machine (1-group, used or new) | 3000 | 4500 | 6500 | No | Used La Marzocco / ECM ~RM 4,500
2.03 | Espresso grinder (Eureka / Niche) | 1500 | 1800 | 2800 | No | Filter grinder = Phase 1 Comandante
2.04 | Brewing tools — espresso accessories only (tamper, distrib, knockbox) | 200 | 350 | 550 | No | V60s/Origami/scales/kettle from Phase 1
2.05 | Initial green coffee inventory (top-up beyond P1 trip) | 800 | 1200 | 1800 | Partial | P1 trip brought 5–8 kg; this is the top-up
2.06 | Co-roasting first 2 months (CR KL) | 800 | 1200 | 1800 | No | 1 session/wk × 8 weeks at RM 100–225/session
2.07 | Brand photography day shoot | 600 | 900 | 1300 | No | Brand identity already paid in P1 — only photo here
2.08 | Packaging — cups, sleeves, bags first production run | 800 | 1000 | 1500 | No | 1,000 units first run
2.09 | Cold brew kegs + cold brew kit | 200 | 350 | 500 | No | 5L mini-keg ×2
2.10 | Marketing launch (boost, micro-influencer) | 400 | 600 | 1000 | No | IG/TikTok boosted posts month 1
2.11 | Soft-launch venue sublet (1–2 events) | 200 | 350 | 600 | No | Friend cafe sublet
2.12 | Cart consumables first month (milk, water, etc.) | 300 | 450 | 700 | No | First-month operating
2.13 | Equipment service / first-month maintenance reserve | 100 | 200 | 350 | No | Backflush cleaner, gaskets, tools
2.14 | Contingency (10% of itemised) | 930 | 1370 | 2090 | No | Standard 10% buffer
| Phase 2 GROSS capex (before P1 carry-over credit) | 10230 | 15070 | 22990
| Less: Reusable equipment from Phase 1 (already paid) | -5430 | -7570 | -10440
| PHASE 2 NET CAPEX (new spend in Phase 2) | 4800 | 7500 | 12550

## 6. Combined Capex
COMBINED CAPEX — Phase 1 + Phase 2 vs RM 15K Budget
The honest "what does it really cost to launch KNNO?" view. v2 reflects your full prep list.
Component | Bear | Base | Bull | Notes
Phase 1 NET equipment burn (true cost lost) | 5770 | 9491 | 13300 | Out-of-pocket less reusable equipment
Phase 1 Reusable equipment (becomes Phase 2 capex) | 5430 | 7570 | 10440 | Cart, drippers, grinder, kettle, scales, brand ID, banner, seats, tables
Phase 2 NET capex (new spend after carry-over) | 4800 | 7500 | 12550 | Espresso, photography, packaging, marketing, etc.
TOTAL LAUNCH CAPEX (P1 burn + P1 reusable + P2 net) | 16000 | 24561 | 36290 | The honest number
Less: Phase 1 carboot revenue offset | -1200 | -2300 | -4510 | Carboot sales partially fund the launch
NET LAUNCH CAPEX after carboot revenue | 14800 | 22261 | 31780 | What you actually need in the bank
Available capital (your RM 15K) | 15000 | 15000 | 15000 | Per the brief
Surplus / (Shortfall) vs RM 15K | -14800 | -22261 | -31780 | Negative = need more capital or trim
% of capital used | #DIV/0! | #DIV/0! | #DIV/0! | >100% = over-budget
Funding Status (Base scenario)
Status flag | SEVERE SHORTFALL — re-evaluate scope
Trim Options (apply if base shows shortfall)
Trim option | Saves | Trade-off
Buy used espresso machine (vs new) | ~RM 1,500–2,500 | Quality risk; service network harder
Cart with water pump but NO sink (use 5L water tank) | ~RM 500–800 | Less convenient cleanup at venue
Defer espresso entirely until month 3 (manual brew launch) | ~RM 4,500+ | Possible if Phase 1 shows manual handles cup count
Trim packaging first run from 1,000 to 500 units | ~RM 400–600 | More frequent reorders
Defer brand photo shoot to month 2 | ~RM 600 | Use Phase 1 carboot photos as launch material
Sole Prop instead of Sdn Bhd | ~RM 900 | Less liability protection; still legally OK for cart-format
3 V60s instead of 4 (skip Origami) | ~RM 200 | Lose process variety
Foldable seats only — skip tables | ~RM 300 | Less customer dwell setup

## 7. Decision Gate
PHASE 1 → PHASE 2 DECISION GATE — Weighted Scoring
Run after all 4 carboot pop-ups. Enter ACTUALS in BLUE column F. Score auto-classifies GO / HOLD / NO-GO.
# | Criterion | Weight | Target | Direction | Actual | Score | Notes
G.1 | Total cups served (across 4 pop-ups) | 15% | 200 | higher | 200 | 100% | Bear=120 · Base=200 · Bull=280
G.2 | Stop-rate at unfamiliar venues (% of foot traffic) | 15% | 8% | higher_pct | 8% | 100% | Strangers stopping; not friends
G.3 | Repeat faces named (came back 2+ times) | 10% | 12 | higher | 12 | 100% | Critical leading indicator
G.4 | Avg ticket (RM/cup) | 8% | 13 | higher_curr | 13 | 100% | Confirms RM 12+ price tolerance
G.5 | Cup quality score (% of cups ≥3/4 internal) | 12% | 75% | higher_pct | 75% | 100% | Internal cupping during Phase 1
G.6 | Critical defects served (count) — INVERTED | 8% | 0 | lower | 0 | 100% | Any > 0 reduces score; target = zero
G.7 | Founder enjoyment avg (1–10) | 12% | 7 | higher | 7 | 100% | Burnout / sustainability check
G.8 | Sustainable workload — both could do 3 days/wk? (1=Yes, 0=No) | 10% | 1 | binary | 1 | 100% | Honest answer
G.9 | Indonesian-roasted vs CR KL cup parity (1=parity, 0=not) | 5% | 1 | binary | 1 | 100% | Validates Indonesia R&D approach
G.10 | QR scan rate per cup (% of customers) | 5% | 30% | higher_pct | 30% | 100% | Validates funnel into bag sales / IG
| Weights sum check (must = 100%) | 100%
| TOTAL WEIGHTED SCORE |  |  |  |  | 100%
| DECISION | GO — proceed to Phase 2 with confidence
Threshold Reference
| ≥ 85% | GO — proceed to Phase 2 with confidence
| 70–84% | GO with cautions — address weakest criteria first
| 55–69% | HOLD — re-test 2 weeks with adjusted variables
| < 55% | NO-GO — consider pivot to online-only OR extend validation 4–6 weeks
Diagnostic: Worst-Performing Criteria
| Lowest score | 100% | Number of criteria below 50% |  | 0
Note: defaults are set to TARGETS so the workbook opens at "GO with confidence." Replace BLUE actuals with real measurements after Phase 1 pop-ups.

## 8. P1 Risks
PHASE 1 RISK REGISTER — Indonesia trip + Carboot specifics
Likelihood (1–5) × Impact (1–5) = Score (out of 25). ≥15 = critical, 9–14 = high, 4–8 = medium, ≤3 = low.
# | Risk | Likelihood (1–5) | Impact (1–5) | Score | Mitigation | Owner | Status
R.01 | Producer cancels in-person visit at last minute | 3 | 4 | 12 | Confirm in writing 14d ahead; backup producer; rental roastery as Plan B | F1 | Open
R.02 | Customs / personal import issue with roasted/green | 2 | 4 | 8 | Verify MOH+Customs rules pre-flight; declare honestly; carry receipts; volume kept clearly personal | F1 | Open
R.03 | F1 illness during Indonesia trip | 2 | 5 | 10 | Travel insurance; F2 pre-briefed on venue logistics; carboot can defer 1 wk | Both | Open
R.04 | Indonesian roastery quality inadequate (no curve logging, drum issues) | 3 | 4 | 12 | Visit roastery before paying; rental roastery as Plan B; bring own thermometer/scale | F1 | Open
R.05 | Carboot venue cancellations (last-minute) | 3 | 3 | 9 | 5–6 venue options; confirm 48h ahead; Plan B per event | F2 | Open
R.06 | Coffee cart fabrication delayed (pump/sink integration takes longer) | 3 | 4 | 12 | Order cart Week -7; have backup folding-table fallback for first 1–2 pop-ups | F2 | Open
R.07 | Beans damaged/stale by time they reach MY | 2 | 4 | 8 | Vacuum-pack within 24h of roast; ship within 5 days; cup test within 7 days | F1 | Open
R.08 | F2 burnout from solo work in MY weeks -6/-5 | 4 | 3 | 12 | Pre-load tasks into Week -7; daily 15-min sync; no new commitments | F2 | Open
R.09 | DBKL Roving Hawker permit denied or delayed | 3 | 4 | 12 | Submit application Week -8; use friend-cafe carparks (covered by their licence) as fallback for first pop-ups | F2 | Open
R.10 | Typhoid jab + food handling cert delays | 2 | 3 | 6 | Book both founders in Week -8 (KKM clinics); typically 1 week turnaround | Both | Open
R.11 | Brand identity not delivered in time for banner | 4 | 3 | 12 | Designer engaged Week -8 (one week earlier than original plan); brief is light (logo + 2 colours + type) | F2 | Open
R.12 | Equipment damage / loss during travel (Indonesia ↔ MY) | 2 | 3 | 6 | Carry-on valuables; checked-baggage insurance; minimal equipment to/from Indonesia | F1 | Open
R.13 | Currency loss (IDR drops vs MYR while paying cash) | 2 | 2 | 4 | Convert in tranches; use Wise / Aspire; carry cash + card backup | F1 | Open
R.14 | F1 misses flight back (rebooking cost) | 1 | 3 | 3 | Buy flexible-fare; build 1-day buffer; airport accommodation booked | F1 | Open
R.15 | Friends-only crowd at carboot = false-positive validation | 4 | 4 | 16 | Pop-up #1 (office tower) skewed strangers by design; track friend vs stranger separately | Both | Open
R.16 | Weather kills outdoor carboot venue | 3 | 3 | 9 | Mix indoor + outdoor venues; 1-day-ahead reschedule policy; weather check 24h prior | Both | Open
R.17 | Phase 1 takes longer than 3 weeks | 3 | 4 | 12 | Buffer 1 week; if >4 weeks: defer Phase 2 launch by same amount | Both | Open
R.18 | Phase 1 results inconclusive (mixed signals) | 3 | 3 | 9 | Pre-defined scoring (sheet 7); quantify; HOLD path = re-test, not pivot | Both | Open
R.19 | Indonesian producer relationship damaged by amateur visit | 2 | 4 | 8 | Pay producer fairly; bring small gift; follow-up thank-you within 7 days | F1 | Open
R.20 | Roasted beans land tasting clearly worse than expected | 3 | 4 | 12 | Sample roast 2 lots in Indonesia, cup before flying back; if poor → 2nd producer or KL co-roast for 1B/1C | F1 | Open
R.21 | Pop-up #1 (office) underwhelms — F1 morale tanks | 3 | 2 | 6 | Pre-frame as warmup, not validation; analyse week-end | Both | Open
R.22 | Phase 1 capex blows past RM 8K (cart costs, certs) | 3 | 4 | 12 | Lock cart spec by Week -7; trim options ready (sink-less cart, 3 V60s, no Origami) | Both | Open
R.23 | Public liability claim during carboot (slip, burn, allergy) | 1 | 5 | 5 | Insurance from Week -8; ice/burn first aid kit; allergen disclosure on banner | Both | Open
Risk Register Summary
| Total risks tracked | 23
| Critical risks (score ≥15) | 1
| High risks (score 9–14) | 13
| Medium risks (score 4–8) | 8
| Low risks (score ≤3) | 1
| Aggregate risk exposure (sum of scores) | 215
| Average risk score | 9.3478

## 9. P1 Sensitivity
PHASE 1 SENSITIVITY — Carboot Revenue (cups × ticket × 4 events)
What-if matrix: cups served per pop-up × avg ticket = total Phase 1 revenue. Highlight = % of Phase 1 cost recovered.
Phase 1 base cost (out-of-pocket, RM): | 17061
Number of pop-ups: | 4
REVENUE MATRIX (RM) | Avg ticket (RM/cup) →
Cups per pop-up ↓ | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 18
15 | 600 | 660 | 720 | 780 | 840 | 900 | 960 | 1080
20 | 800 | 880 | 960 | 1040 | 1120 | 1200 | 1280 | 1440
25 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1800
30 | 1200 | 1320 | 1440 | 1560 | 1680 | 1800 | 1920 | 2160
35 | 1400 | 1540 | 1680 | 1820 | 1960 | 2100 | 2240 | 2520
40 | 1600 | 1760 | 1920 | 2080 | 2240 | 2400 | 2560 | 2880
45 | 1800 | 1980 | 2160 | 2340 | 2520 | 2700 | 2880 | 3240
50 | 2000 | 2200 | 2400 | 2600 | 2800 | 3000 | 3200 | 3600
60 | 2400 | 2640 | 2880 | 3120 | 3360 | 3600 | 3840 | 4320
70 | 2800 | 3080 | 3360 | 3640 | 3920 | 4200 | 4480 | 5040
80 | 3200 | 3520 | 3840 | 4160 | 4480 | 4800 | 5120 | 5760
Legend:
Green | Carboot revenue ≥ Phase 1 base cost (full recovery)
Yellow | Partial recovery (60–99% of Phase 1 cost)
Red | Low recovery (<60% of Phase 1 cost)
Reading the matrix
• Phase 1 cost is now ~RM 8–12K (your prep list). Full revenue recovery requires ~80 cups × RM 18+ across 4 pop-ups — not realistic at carboot prices.
• Phase 1 is NOT designed to break even. The matrix shows whether revenue covers the OPS cost of 1C (~RM 1K), not the equipment investment.
• GREEN cells signal Phase 4 (Public Launch) economics will likely beat the optimistic scenario in [[09-Financial Projections (Conservative)]].
• Most of the Phase 1 spend is RECOVERABLE EQUIPMENT (carries to Phase 2) — the true "lost" cost is much smaller.

## 10. Cash Tracker
WEEK-BY-WEEK CASH TRACKER (Base scenario, v2)
Running cash position from Week -8 through Week +12. Updated for v2 prep list (higher Phase 1 outflow).
Starting capital (RM): | 15000
Week | Date range | Activity | Inflow | Outflow | Net cash | Notes
W -8 | May 4–10 | Foundation: legal, brand brief sent, certs booked, accounts | 0 | 600 | 14400 | Bank acct, domain, typhoid jab + food handler course bookings
W -7 | May 11–17 | Foundation: suppliers, Indonesia trip booked, cart ordered, designer engaged | 0 | 4500 | 9900 | Indonesia flight + cart deposit (RM 1.5K) + designer deposit + permit fees
W -6 | May 18–24 | Indonesia week 1 + MY parallel work | 0 | 3500 | 6400 | F1 in Indonesia (accom, food, roastery, green) + cart final payment + drippers/grinder/kettle
W -5 | May 25–31 | Indonesia week 2 + Carboot Pop-up #1 | 700 | 2200 | 4900 | F1 returns; Pop-up #1 small office crowd; banner printed; remaining equipment
W -4 | Jun 1–7 | Carboot Pop-ups #2, #3, #4 + Decision Gate | 1900 | 800 | 6000 | 3 pop-ups ~50 cups avg × RM 13
W -3 | Jun 8–14 | Phase 2 Build: espresso machine + grinder + green top-up | 0 | 6500 | -500 | Major Phase 2 capex item — espresso + grinder
W -2 | Jun 15–21 | Phase 2 Build: 1st production roast, packaging, photo shoot | 0 | 2200 | -2700 | Co-roasting + packaging first run + photography
W -1 | Jun 22–28 | Phase 2 Build: cart finish, drill, soft launch booking | 0 | 1500 | -4200 | Cart finishing/upgrade + sundries + soft-launch venue + insurance balance
W 0 | Jun 29 – Jul 5 | PHASE 3: Soft launch + Phase 4 launch week | 700 | 400 | -3900 | Soft launch invitee revenue (40 cups × RM 16)
W +1 | Jul 6–12 | PHASE 4: Public launch — 1st pop-up | 720 | 500 | -3680 | ~45 cups × RM 16; venue + roast
W +2 | Jul 13–19 | 2nd public pop-up + online drop launch | 1100 | 550 | -3130 | Cup + bag online drop
W +3 | Jul 20–26 | 3rd & 4th pop-ups, weekly review settled | 1500 | 600 | -2230 | Cadence locked
W +4 | Jul 27 – Aug 2 | Continued cadence | 1500 | 600 | -1330
W +5 | Aug 3–9 | Aug rhythm | 1600 | 700 | -430 | 2nd signature lot launch
W +6 | Aug 10–16 |  | 1700 | 700 | 570
W +7 | Aug 17–23 |  | 1700 | 700 | 1570
W +8 | Aug 24–30 | Quarterly pre-mortem | 1700 | 800 | 2470 | Insurance renewal + service
W +9 | Aug 31 – Sep 6 |  | 1800 | 700 | 3570
W +10 | Sep 7–13 |  | 1800 | 700 | 4670
W +11 | Sep 14–20 |  | 1800 | 800 | 5670 | Aceh harvest forward-buy starts
W +12 | Sep 21–27 |  | 1900 | 800 | 6770
|  | Totals (W -8 → W +12) | 22120 | 30350 | 6770
|  | Lowest cash position (cash floor): |  |  | -4200
|  | Week of cash floor: |  |  | W -1
Cash position colour key: GREEN >RM 3,000 (healthy) · YELLOW RM 0–3,000 (caution) · RED <RM 0 (CRITICAL — out of cash)
Note: with v2 prep list, Phase 1 outflow concentrates in Weeks -7 to -3. Cash floor likely Week -3 (RM ~3K range). If RED appears, you need ~RM 5–8K more capital OR aggressive trim.